## Sprint 1 RTM
Student Attendance Management System (SAMS) — Requirements Traceability Matrix
Version 1.0 ¦ Sprint 1 ¦ Prepared by: Taanya Gupta (QA Lead) ¦ Sources: SRS v1.0, Architecture & Design Specification v1.0, STP v1.0, Sprint 1 Test Cases & Test Data (TASK-002)
Requirement ID | Requirement Summary | Architecture / Design Module | SRS Test Reference | Sprint 1 Test Evidence Mapping | Traceability Status | Evidence / Gap Notes
SAM-F-001 | Authenticate users with valid credentials and establish a role-associated session | Authentication & RBAC | TC-AUTH-01 | TC-001, TC-002, TC-030, TC-037 | Verified for tested checks | Admin valid/invalid login and faculty login passed; student UI login partially verified (TC-037).
SAM-F-002 | Provide role-based access for Admin, Faculty, and Student users | Authentication & RBAC | TC-AUTH-02 | TC-027, TC-029, TC-030, TC-042, TC-044 | Verified for tested checks | Student access to admin audit returned 403; unauthenticated student list returned 401; faculty login and authorization checks recorded.
SAM-F-003 | Allow administrators to add, update, search, activate/deactivate student records | Student Management | TC-STU-01 | TC-004, TC-005, TC-006, TC-007, TC-043 | Verified for tested checks | Student creation/listing passed; invalid email returned 400; duplicate email returned 409. Update/activation/deactivation not separately evidenced in supplied suite.
SAM-F-004 | Allow administrators to create and maintain faculty accounts and profiles | Faculty & Subject Management | TC-FAC-01 | TC-009 | Partially verified | Faculty creation passed; update/activation/deactivation/search not separately evidenced.
SAM-F-005 | Maintain academic terms, subjects, classes/sections and their relationships | Faculty & Subject Management | TC-MASTER-01 | TC-003, TC-008 | Partially verified | Class and subject creation passed; subject creation first encountered a SQLite lock and succeeded on retry. Full relationship/term management not separately evidenced.
SAM-F-006 | Assign faculty to authorized subjects and classes | Faculty & Subject Management | TC-ASSIGN-01 | TC-010, TC-031, TC-032 | Verified for tested checks | Assignment creation and faculty summary/report recorded as passing; explicit unassigned-faculty denial not separately evidenced.
SAM-F-007 | Allow authorized faculty to create attendance sessions | Attendance Management | TC-ATT-01 | TC-011 | Verified | Attendance session created successfully (HTTP 200).
SAM-F-008 | Display enrolled students and allow faculty to mark Present/Absent | Attendance Management | TC-ATT-02 | TC-012, TC-020 | Verified for tested checks | Attendance marked Present and later corrected to Absent; UI evidence is separate and limited.
SAM-F-009 | Prevent duplicate attendance records for the same student/session | Attendance Management; Database | TC-ATT-03 | TC-013, TC-036 | Verified | Duplicate attendance mark returned HTTP 409.
SAM-F-010 | Allow authorized attendance corrections within configured period and record changes | Attendance Management; Audit/Logging | TC-ATT-04 | TC-020, TC-021, TC-025 | Verified for tested checks | Correction succeeded and audit action was visible; correction-window boundary/unauthorized edit tests not fully evidenced.
SAM-F-011 | Calculate overall and subject-wise attendance percentage automatically | Reporting & Analytics | TC-CALC-01 | TC-015, TC-016, TC-037 | Verified for tested checks | Percentage endpoint returned 100% for 1/1 before correction; low-attendance list and student dashboard were observed.
SAM-F-012 | Allow students to view their own attendance summary and detailed history | User Interface; Reporting & Analytics | TC-STU-02 | TC-014, TC-037 | Partially verified | History endpoint passed; desktop student dashboard was observed; mobile not separately tested.
SAM-F-013 | Allow faculty to view summaries and detailed records for assigned classes/subjects | User Interface; Attendance Management | TC-FAC-02 | TC-030, TC-031, TC-032 | Verified for tested checks | Faculty login, attendance summary, and attendance report recorded as passing.
SAM-F-014 | Generate student-, subject-, class-, and date-range attendance reports | Reporting & Analytics | TC-REP-01 | TC-017, TC-026 | Verified for tested checks | Attendance report and date filter returned HTTP 200; every report dimension not individually evidenced.
SAM-F-015 | Identify students below the configured attendance threshold | Reporting & Analytics; Notification/Alert | TC-ALERT-01 | TC-016, TC-025, TC-037 | Verified for tested checks | Low-attendance endpoint and 75% threshold were checked; dashboard showed a student below threshold.
SAM-F-016 | Search and filter attendance by student, subject, class, date, and status | User Interface; Attendance Management | TC-SEARCH-01 | TC-019, TC-026, TC-043 | Verified for tested checks | Status/date filters passed; injection-style search returned an empty result safely. All filter fields not individually evidenced.
SAM-F-017 | Export authorized attendance reports in a configured downloadable format | Reporting & Analytics | TC-EXP-01 | TC-018 | Verified | CSV export returned HTTP 200 in the supplied test suite; tester also reported being able to download CSV.
SAM-F-018 | Maintain audit records for attendance creation/correction, user changes, and configuration changes | Audit/Logging; Database | TC-AUDIT-01 | TC-021, TC-027, TC-044 | Verified for tested checks | Correction audit entry was visible; student access to audit endpoint returned 403. All audit event types not individually evidenced.
SAM-NF-001 | Normal UI requests respond within 3 seconds for at least 90% of requests under normal load | Performance | TC-PERF-01 | TC-033 | Partially verified — limited scope | Only a single local /openapi.json response-time smoke test was recorded; not a formal 90th-percentile test.
SAM-NF-002 | Achieve at least 99% monthly availability excluding scheduled maintenance | Reliability | TC-REL-01 | TC-034 | Partially verified — limited scope | Backend returned HTTP 200 after restart; monthly availability is not established by this smoke test.
SAM-NF-003 | Protect stored credentials using strong one-way hashing; never store plaintext passwords | Security; Authentication & RBAC | TC-SEC-01 | TC-035, TC-041 | Partially verified | PBKDF2-HMAC-SHA256 salted password hash was observed; log-redaction review was limited to backend/main.py.
SAM-NF-004 | Maintain data integrity so attendance cannot reference nonexistent students, sessions, or classes | Database; Attendance Management | TC-DATA-01 | TC-023, TC-024, TC-036 | Verified for tested checks | Unknown session returned 404; student not enrolled returned 400; duplicate attendance returned 409.
SAM-NF-005 | Provide a responsive and understandable interface on desktop and mobile | User Interface | TC-UX-01 | TC-037 | Partially verified | Desktop login/dashboard was observed; mobile viewport has not been separately tested.
SAM-NF-006 | Support maintainable modular code with documented schema, APIs/components, and configuration | Application/Business Logic; API; Database | TC-MAINT-01 | TC-038 | Partially verified — observation | Pytest reported 2 passed and 18 warnings; SRS/SAD document architecture and API design, but modularity review is incomplete.
SAM-NF-007 | Support at least 100 concurrent authenticated users without critical failure | Application/Business Logic; API | TC-LOAD-01 | TC-039 | Partially verified — limited scope | Five simultaneous /openapi.json requests returned HTTP 200; this does not demonstrate 100 authenticated users.
SAM-SR-001 | Enforce HTTPS/TLS for all production communication; redirect or disable insecure HTTP | Security; API/Deployment | TC-SEC-02 | TC-040 | Pending deployment verification | Local development server served HTTP; HTTPS request returned HTTP 000. Verify in deployed environment.
SAM-SR-002 | Store user passwords only as salted, strong one-way hashes | Security; Authentication & RBAC; Database | TC-SEC-03 | TC-035, TC-041 | Partially verified | Salted PBKDF2-HMAC-SHA256 hash was observed; comprehensive log/storage review remains limited.
SAM-SR-003 | Enforce role-based authorization for protected operations | Authentication & RBAC; API | TC-SEC-04 | TC-027, TC-042, TC-044 | Verified for tested checks | Student token to admin-only audit endpoint returned 403; not every protected operation is covered.
SAM-SR-004 | Validate and sanitize user input; use safe handling for queries | API; Application/Business Logic | TC-SEC-05 | TC-006, TC-007, TC-022, TC-023, TC-024, TC-043 | Verified for tested checks | Invalid inputs and unknown IDs were rejected; inspected search used placeholders/arguments. Coverage limited to tested inputs.
SAM-SR-005 | Create protected audit logs for important attendance and administrative changes | Audit/Logging; Database; Security | TC-SEC-06 | TC-021, TC-027, TC-044 | Verified for tested checks | Attendance correction audit was visible; student access to audit was forbidden.
SAM-SR-006 | Terminate or expire inactive authenticated sessions | Authentication & RBAC; Session Management | TC-SEC-07 | TC-028, TC-045 | Verified | Logout invalidated token (re-use returned 401); configured 5-second session timeout expired token after 7 seconds.

## Read Me
RTM Notes and Status Definitions
Status | Meaning
Verified | Supplied test evidence directly supports the requirement for the stated check(s).
Verified for tested checks | Some relevant checks passed; the note column states the limits of the evidence.
Partially verified | Some evidence exists, but one or more acceptance criteria or variations were not separately demonstrated.
Partially verified — limited scope | Only a smoke test was performed; do not treat it as full performance, reliability, or load verification.
Pending deployment verification | The local development environment cannot demonstrate the production/deployment requirement.
Important mapping note | The SRS uses requirement-specific test references such as TC-AUTH-01 and TC-SEC-02, while the supplied TASK-002 execution suite uses TC-001 through TC-045. The Sprint 1 Test Evidence Mapping column links the closest documented executed cases; these are not asserted to be identical test IDs. Where the evidence does not prove the full acceptance criterion, the status is deliberately qualified.
Before merging | Review the mapping with the team, especially the items marked partially verified or pending. Keep statuses evidence-based. The RTM is a traceability artifact; it does not mean every Sprint 1 or SRS requirement is fully implemented.